# General Plan

# 🍽️ Project Plan – Smart Meal Suggestion App

# 0️⃣ Team Structure (4 People – Clear Ownership)

### Rule

Each feature has:

- 1 Owner

- 1 Reviewer

- Nothing merges without review.

### Roles

Nicolas (neb22b)
Tech Lead + Backend Lead

- Architecture

- Backend APIs

- Database schema

- Deployment

- Integration

Ruth (rb22h)
AI/Safety Lead + Data/Parsing

- Ingredient extraction

- Allergy filtering logic

- Prompt-injection defenses

- AI safety testing

Robert (rfp22)
Frontend Lead (React Native)

- UI/UX

- Navigation

- Pantry + Recipe screens

- Camera/photo flow

Gannon (gw22c)
QA/DevOps + Integration Support

- Test plans

- CI checks

- Bug triage

- Demo script

- Documentation

- Release checklist

# 1️⃣ MVP Scope (LOCK THIS)

## ✅ Must Ship

### 👤 User Account

- Basic auth

- Profile preferences:

  - Allergies

  - Dietary restrictions

  - Disliked ingredients

  - Skill level

  - Tools

### 🧊 Pantry / Inventory

- Add / edit / remove ingredients

- Optional quantity

- Optional expiration

### 🍳 Meal Suggestions

- Uses pantry + time + tools + skill

- Returns 3–10 recipes

- Shows match % + missing items

### 🚨 Allergy & Restriction Safety (Hard Filter)

- Recipes violating allergies are NEVER shown

- Or shown only with safe substitution

### 🔁 Ingredient Substitutions

- Suggests safe alternatives

### 📸 Photo Input (Basic)

- Upload ingredient photo or nutrition label

- Extract ingredient candidates

- User confirms before adding

## 🌱 Stretch Goals (Only if Stable)

- Expiration reminders

- Macro tracking

- Cook mode (step-by-step timer)

- Auto grocery list

# 2️⃣ System Architecture

## Stack

- Mobile: React Native (Expo OK)

- Backend: Python (FastAPI recommended)

- Database: PostgreSQL

- AI Layer:

  - Recipe API (Spoonacular / Edamam)

  - Ranking + substitutions (rules first, optional LLM)

## Service Boundaries

### 📱 Mobile App

- Auth UI

- Pantry UI

- Preferences UI

- Suggestions + recipe display

- Photo upload

### 🖥 Backend API

- Auth endpoints

- Pantry CRUD

- Suggestion endpoint

- Substitution endpoint

- Photo extraction endpoint

## 🔒 Safety by Design

- Use structured recipe API data

- LLM never invents safety claims

- Hard restriction filter always runs after AI

# 3️⃣ Work Breakdown Structure (WBS)

## A) Backend & Database

Owner: Nicolas | Reviewer: Ruth

### A1 – Setup

- FastAPI scaffold

- Docker Compose (Postgres + backend)

- /health endpoint

### A2 – DB Schema

Tables:

- users

- user_preferences

- inventory_items

- recipe_cache (optional)

### A3 – API Endpoints

- POST /auth/register

- POST /auth/login

- GET/POST/PUT/DELETE /inventory

- GET/PUT /preferences

- POST /suggest

- POST /substitute

- POST /photo/extract

### A4 – Suggestion Pipeline

- Query recipe API

- Normalize ingredients

- Compute match score

- Apply restriction filter

- Return sorted list

Deliverables:

- OpenAPI docs

- Postman / curl examples

## B) AI + Safety + Parsing

Owner: Ruth | Reviewer: Nicolas

### B1 – Ingredient Normalization

- Lowercase

- Remove punctuation

- Singularize plurals

- Synonym map

### B2 – Restriction Engine (Hard Rules)

Output:

- PASS

- FAIL

- PASS_WITH_SUBS

### B3 – Substitution Engine

Rules-based first:

- Dairy-free → milk → oat milk

- Gluten-free → soy sauce → tamari

- Nut allergy → peanut oil → vegetable oil

LLM suggestions must:

- Be validated

- Not violate allergy list

### B4 – Prompt Injection Defenses

- Strict JSON output

- Reject non-JSON

- Post-validation

- Keys server-side only

### B5 – Photo Extraction

- OCR or label parsing

- Detect “Ingredients:” line

- Return candidates + confidence

- User confirms

Deliverables:

- Unit tests

- Safety checklist doc

## C) Mobile App

Owner: Robert | Reviewer: Gannon

### C1 – App Skeleton

Screens:

- Login/Register

- Pantry

- Preferences

- Suggestions

- Recipe Detail

- Camera/Upload

### C2 – Pantry UI

- Add/edit/remove

- Search

- Toggle fridge/pantry

### C3 – Preferences UI

- Allergies

- Diet

- Tools

- Skill level

### C4 – Suggestions UI

- Inputs: time, portions

- Recipe cards with:

  - Match %

  - Missing items

  - Substitution tags

### C5 – Photo Flow

- Capture/upload

- Confirm extracted items

- Add to pantry

Deliverables:

- Demo flow

- Loading + error states

## D) QA / CI / Documentation

Owner: Gannon | Reviewer: Robert

### D1 – QA Plan

- Auth tests

- Inventory tests

- Suggestion tests

- Restriction tests

- Photo tests

### D2 – CI

- Linting

- Backend unit tests

- Optional mobile build check

### D3 – Bug Tracking

- GitHub issue templates

- Sprint board

### D4 – Documentation

- README

- Setup instructions

- Architecture diagram

- API examples

- Known limitations

### D5 – Demo Prep

- Demo script

- Seed data

- Backup recording

# 4️⃣ Sprint Plan (5 Sprints)

### Sprint 0 – Setup

Backend + mobile scaffold + CI
Exit: everything boots

### Sprint 1 – Auth + Pantry

Full CRUD working
Exit: end-to-end pantry flow

### Sprint 2 – Preferences + Restrictions

Restriction engine deterministic
Exit: PASS/FAIL works correctly

### Sprint 3 – Suggestions + Substitutions

Recipe API integration
Exit: allergy-safe suggestions

### Sprint 4 – Photo + Polish

Photo extraction
Regression testing
Exit: Full demo flow works

# 5️⃣ Weekly Workflow

### Meeting (60–75 min)

- Blockers

- Burndown

- PR review

- Next tasks

- Demo rehearsal

### Async Rules

Every issue must include:

- Description

- Acceptance criteria

- Owner + reviewer

PRs must include:

- What changed

- How to test

- Screenshot or curl example

# 6️⃣ Allergy-Safe Acceptance Criteria (Non-Negotiable)

Block recipe if:

- Ingredient matches allergy

- “May contain” tag

- Unsafe LLM substitution

Allow only if:

- Safe dictionary substitute exists

- Substitute respects all constraints

- UI labels: “Modified recipe (substitution applied)”

# 7️⃣ Professor-Ready Deliverables

- SRS-lite (2–4 pages)

- Architecture diagram

- OpenAPI spec

- Test plan + results

- Demo script

- Risk log + mitigations

# Task List

## Step-by-step (ordered)

### 1) Repo + rules + local run working (Day 1–2)

- Gannon (Owner): Create GitHub repo, branching rule (PR required), issue templates, basic Kanban columns.

- Nicolas (Owner): Backend FastAPI scaffold + Docker Compose (backend + Postgres) + /health.

- Robert (Owner): React Native app scaffold + navigation skeleton.

- Ruth (Owner): Start restriction rules list + substitution starter dictionary.

- Reviewers: Gannon reviews Robert, Robert reviews Gannon, Ruth reviews Nicolas, Nicolas reviews Ruth.

Exit: app boots, backend boots, DB connects, CI runs.

### 2) Database schema + API contracts (Day 2–4)

- Nicolas (Owner): Postgres schema + migrations.

- Robert (Owner): Write the frontend data models + API client stubs.

- Gannon (Owner): “how to run” README + Postman/curl examples.

- Reviewer: Ruth reviews schema/API shapes for safety fields.

Exit: tables exist + endpoints are agreed (even if mocked).

### 3) Auth end-to-end (Week 1)

- Nicolas (Owner): /auth/register, /auth/login.

- Robert (Owner): Login/Register screens wired to backend.

- Gannon (Owner): Auth test cases + CI runs tests.

- Reviewer: Robert reviews backend auth; Nicolas reviews frontend wiring.

Exit: can register/login from the phone app.

### 4) Pantry CRUD end-to-end (Week 2)

- Nicolas (Owner): /inventory CRUD.

- Robert (Owner): Pantry screen (add/edit/delete/search/location).

- Gannon (Owner): CRUD acceptance tests + bug triage.

- Reviewer: Gannon reviews frontend UX edge cases; Ruth reviews ingredient naming conventions.

Exit: user can manage pantry items fully from app.

### 5) Preferences end-to-end (Week 3)

- Nicolas (Owner): /preferences GET/PUT.

- Robert (Owner): Preferences screen (allergies/diet/tools/skill).

- Ruth (Owner): Define canonical format (arrays, allowed values, synonym handling).

- Reviewer: Nicolas reviews Ruth’s formats; Gannon reviews flows + error handling.

Exit: preferences saved + fetched reliably.

### 6) Build the restriction engine (Week 3–4)

- Ruth (Owner): PASS/FAIL/PASS_WITH_SUBS + synonym map + unit tests.

- Nicolas (Owner): Wire restriction engine into backend as a module/service.

- Gannon (Owner): Test matrix of allergy/diet cases.

- Reviewer: Nicolas reviews restriction logic; Ruth reviews integration correctness.

Exit: given a recipe ingredient list + user prefs, results are deterministic + tested.

### 7) Suggestions pipeline (Week 4–5)

- Nicolas (Owner): /suggest hits recipe API + ranks match % + applies restriction filter.

- Ruth (Owner): Match scoring normalization rules (ingredient cleanup/synonyms).

- Robert (Owner): Suggestions list UI + recipe detail UI (match %, missing items, safety tags).

- Gannon (Owner): End-to-end test scenarios (blocked recipes never shown).

- Reviewer: Ruth reviews “blocked vs allowed” behavior; Robert reviews backend response shape.

Exit: suggestions show up in app and unsafe ones are blocked.

### 8) Substitution engine (Week 5–6)

- Ruth (Owner): Rules-based substitutions + validation (never violates allergies).

- Nicolas (Owner): /substitute endpoint + enforcement checks.

- Robert (Owner): UI labels “Modified recipe (substitution applied)” + show substitution list.

- Gannon (Owner): Tests for substitution safety.

- Reviewer: Ruth reviews backend validation; Nicolas reviews substitution dictionary changes.

Exit: substitutions displayed only when safe + clearly labeled.

### 9) Photo extract MVP (Week 6–7)

- Robert (Owner): Camera/upload + confirm extracted items UI.

- Nicolas (Owner): /photo/extract endpoint (simple OCR/label parse + candidates).

- Ruth (Owner): Parsing heuristics + confidence + normalization.

- Gannon (Owner): Regression tests + edge cases.

- Reviewer: Gannon reviews UX flow; Ruth reviews extraction quality.

Exit: photo → candidates → user confirms → adds to pantry.

### 10) Polish + docs + final demo (Week 8–9)

- Gannon (Owner): Demo script + seed data + final checklist + test report.

- Nicolas (Owner): OpenAPI docs tidy + error handling + logging.

- Robert (Owner): Loading/error states + UI cleanup.

- Ruth (Owner): Safety checklist + final safety tests.

- Reviewer: Everyone reviews demo flow.

Exit: reliable full demo: login → pantry → prefs → suggest → recipe → photo add.

# Nico

# 👨‍💻 Nicolas – Backend / Tech Lead Plan

## Week 1

- Scaffold FastAPI project

- Setup Docker (backend + Postgres)

- Create DB schema

- Implement /auth endpoints

## Week 2

- Build /inventory CRUD

- Add validation logic

## Week 3

- Implement /preferences endpoint

- Integrate restriction engine from Ruth

## Week 4–5

- Integrate recipe API

- Build /suggest endpoint

- Implement match % ranking

- Apply restriction filter before returning results

## Week 6

- Build /substitute endpoint

- Enforce safety validation on substitutions

## Week 7

- Implement /photo/extract endpoint

## Week 8–9

- Add logging + structured error handling

- Finalize OpenAPI docs

- Help stabilize demo flow

# Ruth

# 🤖 Ruth – AI / Safety Lead Plan

## Week 1

- Define canonical ingredient format

- Start normalization function

- Draft restriction rule list

## Week 2

- Finalize normalization logic

- Build synonym dictionary v1

## Week 3

- Implement restriction engine (PASS / FAIL / PASS_WITH_SUBS)

- Write unit tests for allergy/diet edge cases

## Week 4–5

- Define match scoring normalization rules

- Review suggestion filtering logic for safety

## Week 6

- Build rules-based substitution dictionary

- Implement validation layer (never allow unsafe ingredient)

- Add unit tests for substitution safety

## Week 7

- Build ingredient extraction parsing logic

- Normalize extracted ingredients

## Week 8–9

- Final safety checklist document

- Edge-case validation pass before demo

# Robert

# 📱 Robert – Frontend Lead Plan

## Week 1

- Scaffold React Native app

- Setup navigation

- Create API client layer

- Build Login/Register screens

## Week 2

- Build Pantry screen (add/edit/delete/search)

- Connect pantry to backend

## Week 3

- Build Preferences screen

- Multi-select allergies/diets/tools

## Week 4–5

- Build Suggestions screen (recipe cards + match %)

- Build Recipe Detail screen

- Display missing ingredients

## Week 6

- Show substitution tags

- Add “Modified recipe” safety label

## Week 7

- Implement camera/upload flow

- Build confirm extracted items screen

## Week 8–9

- Add loading + error states everywhere

- UI polish

- Ensure full demo flow is smooth

# Gannon

# 🧪 Gannon – QA / DevOps Lead Plan

## Week 1

- Setup GitHub issue templates

- Setup CI (lint + backend tests)

- Draft QA test matrix

## Week 2

- Write auth + inventory acceptance tests

- Track and triage bugs

## Week 3

- Write restriction engine test cases

- Verify deterministic PASS/FAIL behavior

## Week 4–5

- End-to-end suggestion testing

- Confirm allergy-violating recipes never appear

## Week 6

- Write substitution safety test cases

## Week 7

- Regression testing (photo flow + all previous features)

## Week 8–9

- Final regression test pass

- Prepare demo script

- Seed demo data

- Write README + documentation

- Create final test report